## Style Guide
H1 | Inter | 44px | 40px | 36px | 30px | 24px | 800 | H1
H1 | Inter | 48px | 43px | 38px | 30px | 21px | 800 | Large H1
H1 | Inter | 42px | 38px | 34px | 28px | 24px | 800 | Small H1
H2 | Inter | 34px | 30px | 27px | 23px | 21px | 800 | H2
H2 | Inter | 32px | 28px | 25px | 22px | 21px | 800 | Small H2
H3 | Inter | 24px | 22px | 21px | 20px | 19px | 700 | H3
H4 | Inter | 21px | 20px | 19px | 18px | 17px | 800 | H4
H5 | Inter | 19px | 18px | 17px | 17px | 17px | 800 | H5
H6 | Inter | 17px | 17px | 16px | 16px | 16px | 700 | H6
p | Inter | 17px | 17px | 16px | 16px | 16px | 400 | p
p | Inter | 21px | 19px | 18px | 17px | 16px | 400 | Large p
Subtitle | Inter | 14px | 14px | 14px | 14px | 14px | 600 | Subtitle
Button | Inter | 16px | 16px | 16px | 16px | 16px | 700 | Button

## Timeline - HTML including Page
Page Name | Start Date (Development) | End Date (Development) | Developer | Status | Page URL | Dev comment
Theme Setup | 30/04/2025 | 2025-01-05 | Devanshi | Working
Header - Footer | 2025-02-05 | 2025-05-05 | Divya
Home Page | 2025-06-05 | 2025-08-05 | Divya
Top Level Page | 2025-09-05 | 13/05/2025 | Devanshi
Second Level Page | 14/05/2025 | 16/05/2025 | Divya
Blog Index Page | 19/05/2025 | 19/05/2025
Blog Individual page | 20/05/2025 | 21/05/2025

## Pre Launch
Important Note for pre Launch :-
We need to remove the `<meta name="robots" content="noindex, nofollow">` tag before going live.
All dummy pages need to be deleted before going live.
We need to add meta descriptions and titles before going live, and this content will be required from the client.
All URL links need to be verified before going live.
We need to link all items in the header and footer, and for any external URLs, approval from the client will be required, along with confirmation on where they want the links to redirect.
Wherever there is dummy text, such as in the FAQ section, the client will need to provide the proper content, otherwise the page should be hidden for launch.